## Sheet1
#item	Item to complete	Status	Date
1	Add menu to manage categories	completed	11/13/15
2	add feature to display categories	completed	11/13/15
3	Add feature to display orders	completed	11/10/15
4	add user name and date on menu screens	completed	11/10/15
5	remove debug echo statements
6	remove commented code
7	clean up admin checks
8	prevent users accessing screens without login	completed	11/13/15
9	remove unused code
10	Auto decrement when orders are completed	completed	11/11/15
11	do not display products that have quantity < =0 or unavailable	completed	11/11/15
12	when order is complete, change status from partial to completed	completed	11/11/15
13	Consolidate code DRY
14	clear cart after purchase	completed	11/12/15
15	change button to return from show cat to admin menu	completed	11/12/15
16	manage customers